## Sheet1
| Task Name | Baseline Duration | Baseline Start | Baseline Finish | % Complete | Actual Start | Actual Finish | Start Variance | Finish Variance | Predecessors | Resource Names
0 | PM-Project Plan MCB Isalmic Bank Data Mart - 2015-11-06-v2.2 | 65 days | Tue 08-11-16 | Sat 28-01-17 | 37% | Fri 12-11-16 | NA | 0 days | 8.25 days
2 | Concept | 2 days | Tue 08-11-16 | Wed 09-11-16 | 89% | Fri 12-11-16 | Sat 13-11-16 | 0 days | 0 days
3 | Business Case | 1 day | Tue 08-11-16 | Tue 08-11-16 | 100% | Fri 12-11-16 | Fri 12-11-16 | 0.25 days | 0 days
4 | Project Charter | 1 day | Wed 09-11-16 | Wed 09-11-16 | 100% | Sat 13-11-16 | Sat 13-11-16 | 0.25 days | 0 days
7 | Initiation C& Planning | 4 days | Thu 10-11-16 | Mon 14-11-16 | 85% | Mon 14-11-16 | Wed 23-11-16 | 0.25 days | 0 days
8 | Kick Off Meeting | 1 day | Thu 10-11-16 | Thu 10-11-16 | 100% | Mon 14-11-16 | Mon 14-11-16 | 0.25 days | 0 days
9 | Resource Planning | 3 days | Fri 11-11-16 | Mon 14-11-16 | 100% | Tue 15-11-16 | Wed 23-11-16 | 0.25 days | -7 days
12 | Analysis | 17 days | Tue 15-11-16 | Thu 15-12-16 | 71% | Thu 24-11-16 | NA | 0.25 days | 0.25 days
13 | Project Plan | 4 days | Tue 15-11-16 | Wed 23-11-16 | 100% | NA | NA | 0.25 days | 0 days
14 | Business Requirements | 10 days | Thu 24-11-16 | Sat 03-12-16 | 100% | Thu 15-12-16 | Thu 26-12-16 | 0.25 days | 0 days
| BRD review sign off | 1 day | Sat 03-12-16 | Sun 04-12-16 | 100% | NA | NA
15 | Proposed Soloution | 2 days | Mon 12-12-16 | Tue 13-12-16 | 100% | NA | NA | 0.25 days | 5 days
16 | Test Strategy | 2 days | Wed 14-12-16 | Thu 15-12-16 | 100% | NA | NA | 5.25 days | 5 days
25 | Design | 16 days | Fri 16-12-16 | Sun 01-01-17 | 1% | NA | NA | 4.25 days | 8.25 days
26 | Logical Data Model (LDM) | 4 days | Fri 16-12-16 | Tue 20-12-16 | 5% | NA | NA | 4.25 days | 8.25 days
27 | Physical data Model (PDM) | 4 days | Wed 21-12-16 | Sun 25-12-16 | 0% | NA | NA | 8.25 days | 8.25 days
29 | Source to Target Matrix (SMX) | 4 days | Mon 26-12-16 | Thu 29-12-16 | 0% | NA | NA | 8.25 days | 8.25 days
30 | Test Plan Design (TPD) | 2 days | Fri 30-12-16 | Sat 31-01-16 | 0% | NA | NA | 8.25 days | 8.25 days
33 | Review & Sign-Off | 2 days | Sat 31-01-16 | Sun 01-01-17 | 0% | NA | NA | 8.25 days | 8.25 days
34 | Development | 19 days | Mon 02-01-17 | Fri 31-01-17 | 0% | NA | NA | 8.25 days | 8.25 days
35 | Staging ETL Jobs | 10 days | Mon 02-01-17 | Wed 11-01-17 | 0% | NA | NA | 8.25 days | 8.25 days
36 | Tranformation Layer | 10 days | Thu 12-01-17 | Sat 21-01-17 | 0% | NA | NA | 8.25 days | 8.25 days
37 | Data Mart ETL Jobs | 10 days | Mon 23-01-17 | Fri 31-01-17 | 0% | NA | NA | 8.25 days | 8.25 days
38 | Testing | 5 days | Wed 08-02-17 | Tur 14-02-17 | 0% | NA | NA | 8.25 days | 8.25 days
39 | System Integration Testing (SIT) & Bug Fixing | 3 days | Wed 08-02-17 | Fri 10-02-17 | 0% | NA | NA | 8.25 days | 8.25 days
40 | User Acceptance Testing (UAT) & Bug Fixing | 2 days | Mon 13-02-17 | Tue 14-02-17 | 0% | NA | NA | 8.25 days | 8.25 days
41 | Implementation | 3 days | Wed 15-02-17 | Fri 16-02-17 | 0% | NA | NA | 5 days | 5 days
| Implementation plan | 1 days | Wed 15-02-17 | Thu 16-02-17 | 100% | NA | NA | 2days | 2 days
| Code Promotion | 1 days | Wed 15-02-17 | Thu 16-02-17 | 200% | NA | NA | 2days | 3 days
| Final Client Acceptance | 1 day | Fri 16-02-17 | Fri 16-02-17 | 300% | NA | NA | 2days | 4 days